## Sheet1
Project title: Jesmond Library Virtual Noticeboard Bussiness Name: Friends of Jesmond Library, Client Name: Felicity Mendelson Project Manager : Kandakatla Manasa, Asst. Project Manager : Oshomeghie & Research Analyst : Emeka Amuzie
PROJECT PLAN AND TIMELINE STARTED ON 25TH SEPTEMBER, 2023
Deliverables |  |  |  | Planning and Research | [26 empty] | Development and Execution | [29 empty] | Testing
| Assigned to | Start Date | End Date | Progress | WEEK1 | [6 empty] | WEEK2 | [6 empty] | WEEK3 | [6 empty] | WEEK4 | [6 empty] | WEEK5 | [6 empty] | WEEK6 | [6 empty] | WEEK7 | [6 empty] | WEEK8 | [6 empty] | WEEK9 | [6 empty] | WEEK10 | [6 empty] | WEEK11 | [6 empty] | WEEK12
[5 empty] | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
Project Plan -1 - Project Planning and Research |  |  |  |  | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Identifying Technical requirements | Manasa | 2023-09-27 |  | 100% | bar: WEEK1 Wed 27
Evaluating existing website | Oshomeghie | 28/09/2023 - 16/10/2023 |  | 100% | bar: WEEK1 Thu 28 to WEEK4 Mon 16
Define Aim and objectives from existing website | All members | 16/10/2023 to 19/10/2023 |  | 100% | bar: WEEK4 Mon 16 to WEEK4 Thu 19
Identify Key deliverables | Emeka | bar: WEEK4 Mon 16 to WEEK4 Thu 19
Define new functionalities from existing website | All members | bar: WEEK4 Mon 16 to WEEK4 Thu 19
Review security features of the current website | Manasa | bar: WEEK4 Mon 16 to WEEK4 Thu 19
Investigating on hosting, Research on maintenance and Licensing costs | All members | bar: WEEK4 Mon 16 to WEEK4 Thu 19
Project Plan 2 - Project Development and Execution
i Database connection | All members | 20/10/2023 - 14/11/2023 |  | 40% | bar: WEEK4 Thu 19 to WEEK8 Tue 14
Develop Additional features ii.Allow users to bookmark events and then view and delete the bookmarked events | bar: WEEK4 Thu 19 to WEEK8 Tue 14
iii. Allow users to cancel the booked events. | bar: WEEK4 Thu 19 to WEEK8 Tue 14
iv. Adding function that when posters are approved or declined an email automatically. | bar: WEEK4 Thu 19 to WEEK8 Tue 14
v. Email verification for user who registers on the app. | bar: WEEK4 Thu 19 to WEEK8 Tue 14
vi. Database design amendment | bar: WEEK4 Thu 19 to WEEK8 Tue 14
Add below functionalities
i. Add and update events search keywords and categories | Manasa | 20/11/2023 - 27/11/2023 |  | 0% | bar: WEEK9 Mon 20 to WEEK10 Mon 27
ii. Link with google maps to enable events to be searched by location | Oshomeghie | bar: WEEK9 Mon 20 to WEEK10 Mon 27
iii. Present a range of cost options for hosting and maintenance Godaddy, Namecheap & Bluehost etc. | Emeka | bar: WEEK9 Mon 20 to WEEK10 Mon 27
Project Plan -3 Testing
Addressing Security Issues (SSL, Data encryption) | All members | 28/11/2023 - 30/11/2023 |  | 0% | bar: WEEK10 Tue 28 to WEEK10 Thu 30
User Acceptance Testing | All members | 1/12/2023 - 7/12/2023 |  | 0% | bar: WEEK10 Fri 1 to WEEK11 Thu 7
Final Revisions and bug fixes | All members | bar: WEEK10 Fri 1 to WEEK11 Thu 7
Implement web hosting and go live | All members | 2023-12-08 | bar: WEEK11 Fri 8
Project Plan - 4 Documentation
Detailed User Guide Manual | All members | 8/12/2023 - 13/12/2023 |  | 0% | bar: WEEK11 Fri 8 to WEEK12 Wed 13
Final Report | All members | bar: WEEK11 Fri 8 to WEEK12 Wed 13
Handover | All members | 2023-12-15 |  | 0% | bar: WEEK12 Fri 15
Complete
Incomplete
In Progress