## Sheet1
Risk ID | Risk Name | Risk Description | Likelihood | Mitigation
R1 | Scope creep | The project requirements kept changing, adding extra features | Low | The team define clear project scope, conduct regular scope reviews
R2 | Lack of Clear Requirements | Unclear or changing project requirements. | Low | The team conduct detailed requirement gathering sessions, involve stakeholders, document and validate requirements thoroughly.
R3 | Poor Planning | Inadequate project planning, timelines, and resource allocation. | Moderate | The team develop a comprehensive project plan, identify tasks, set realistic timelines, allocate resources effectively, and track progress.
R4 | Technical Challenges | Complexity in implementing specific technologies . | High | The team conduct a technical feasibility study and have contingency plans for technical challenges.
R5 | Inexperienced Team | Lack of expertise among team members. | Low | The team participate in training and skill development programme, encourage knowledge sharing, and mentorship within the team.
R6 | Incomplete System Assessment | Inadequate understanding of the existing system's architecture, functionality, and performance. | Moderate | The team conduct comprehensive meetings with stakeholders, Supervisor, and perform detailed system analysis.
R7 | Security Concerns | Vulnerabilities, data breaches, or unauthorized access. | Moderate | The team implement robust security protocols, encrypt sensitive data, and stay updated with security best practices.
R8 | Third-party Dependencies | Delays, integration challenges | Moderate | The team carefully evaluate third-party services, have backup options in place, and maintain open communication channels with client.
R9 | Budget Overrun | Limited resources, financial strain | High | The team regularly monitor project expenses, explore cost-effective options, negotiate with vendors, and prioritize essential features to avoid budget overruns.
R10 | Server Overload | Website downtime, slow performance | High | Optimize server resources, implement load balancing, conduct performance testing, and consider cloud-based hosting solutions for scalability.
R11 | Database and Server Setup Challenges | Challenges during database and server configuration, potentially leading to project delays and data loss. | High | The team conduct comprehensive meetings with stakeholders, involve end-users, and perform detailed system analysis.
R12 | SSL Implementation Issues | Difficulties in installing and configuring SSL certificates, user trust and security. | Moderate | The team collaborate with security specialists, follow best practices, conduct thorough testing, and ensure timely certificate renewal.
R13 | Inadequate Hosting Resources | Selection of hosting plan without adequate resources, leading to poor website performance. | High | The team thoroughly research hosting providers, select a scalable provider, and choose a plan meeting current and future requirements.
R14 | Incompatible Maintenance Tool | Selection of maintenance solution incompatible with the website's technology stack. | High | The team test solutions in a staging environment, ensure compatibility, and provide comprehensive training to administrators.
R15 | Integration Challenges for New Features | Difficulties in integrating event bookmarking and cancellation features, leading to functionality gaps. | High | The team involve end-users in design, conduct usability testing, and have fallback plans in place for integration failures.
R16 | Security Vulnerabilities in New Features | Insufficient security testing for additional features, leading to potential vulnerabilities. | High | The team implement thorough security testing, follow secure coding practices for vulnerability assessment.
R17 | User Guidance Manual Update | Inaccurate or incomplete documentation | Moderate | The team update the user guidance manual accurately. Conduct internal reviews and user testing on the updated manual to identify and correct inaccuracies before handover.
R18 | Handover Files Preparation | Incomplete or inadequate documentation | Moderate | The team prepare comprehensive handover documentation, including technical specifications, troubleshooting guides. Conduct a thorough review of the handover files with the team and client to ensure completeness and accuracy.
R19 | Delayed Delivery | Missed project deadlines, client dissatisfaction | High | The team monitor project progress closely, identify bottlenecks early, allocate additional resources if necessary, and communicate transparently with the client about potential delays and revised timelines.